## Slide 1: VESI Technical Standards Harmonisation Technical Standards Working Group
19 July 2019(Final)

## Slide 2: Work group members
Anthony James, Technical Standards Manager, CitiPower and Powercor (Lead)
Aza Masoudtehrani, Technical Standards Engineer, CitiPower and Powercor
Jim Tsirikis, Principle Engineer Distribution, United Energy
Max Demko, Senior Engineer, Jemena
Saman De Silva, Principle Engineer, Distribution Standards

## Slide 3: Scope of Technical Standards Harmonisation
Review the civil URD (urban residential development) design and construction standards across all five Victorian Distribution Businesses and where possible align key design and construction parameters across the Victorian Distribution Businesses.
The criteria for alignment will be based on:
Compliance to government regulations and Australian Standards
Least cost, technically acceptable solutions
Constructability
Ease of use and understanding of the standards
In addition to the harmonisation activity the following areas of the standards will also be reviewed1:
CitiPower/Powercor’s2 type 1 & 2 kiosk easements would be reviewed, with the intention of only using type 2 kiosk easements for URDs. This would align with the other distribution businesses.
The potential to install HV cables into conduits for future stages. That is, cables will be capped and then jointed into the future stage.
Decision required:
Endorse project scope
1 As agreed at the Technical Standards Working Group and Construction meeting held on the 5th of July
2 This change only impacts CitiPower/Powercor kiosk reserves, proposed change will align with other DBs

## Slide 4: Deliverables
Gap analysis report outlining difference and commonalities between all five Victorian Distribution Business standards related to URDs
Harmonisation report outlining key design and construction parameters for alignment
Implementation plan & communication strategy for each DB
Implementation of agreed changes to Technical Standards
Decision required:
Endorse deliverables

## Slide 5: Activities
Established Technical Standards working group | 
Determined relevant URD standards across all five DBs | 
Developed gap analysis scope for quotation | 
Obtained quotes from consultants | 
Completed activities
Evaluating quotes from consultants and appointment of successful consultant | 
In progress activity
5/07/2019

## Slide 6: Consultants
Large multinational engineering consultancy
Prior experience undertaking gap analysis for United Energy, CitiPower & Powercor
Positive experience by United Energy, CitiPower & Powercor for prior works
8 weeks to complete analysis
Work to be undertaken by Principle Engineer
Suitability of Principle Engineer is currently being validated
Deliverables are:
  Gap analysis table
  Formal report
  Presentation to stakeholder
  Analysis will provide both the commonalities and differences between the standards
Approximate cost $39,000
Large multinational engineering consultancy
Prior experience undertaking engineering work for UE, CitiPower & Powercor, Jemena and Ausnet
Positive experience by DBs for prior works
However there has been no prior experience with undertaking a gap analysis with DBs
7 weeks to complete analysis
Work to be undertaken by Principle Electrical and Civil Engineer
Suitability of Principle Electrical and Civil Engineer is currently being validated
Deliverables are:
  Formal gap analysis report
  Analysis will provide both the commonalities and differences between the standards
Approximate cost $32,500
Request for quotation was sent to three engineering consultancies:
  Aurecon
  AECOM
  WSP
Offers were received from WSP and AECOM
Aurecon advised that they did not have the capacity to offer the service
Consultancy costs are proposed to be evenly shared among DBs
Decision required:
Endorse delegation to Technical Standards Working Group to make final decision on preferred consultant
Endorse even cost sharing between DBs

## Slide 7: Proposed timeline
Review, comment and endorse the implementation & communication strategy
Gap analysis finding update
12 December 2019
22 November 2019
11 October 2019
Review gap analysis and agree on harmonisation opportunities
Develop implementation plan & communication strategy
1 November 2019
Complete gap analysis
13 September 2019
25 September 2019
Technical Standards Steering Committee
Technical Standards Working Group
Consultant
Technical Standards Steering Committee meeting
Technical Standards Working Group
Technical Standards Steering Committee
Technical Standards Steering Committee meeting
Technical Standards Steering Committee
Decision required:
Endorse proposed timeline
Appoint consultant
12 July 2019
Technical Standards Working Group
Feedback from Technical Standards Steering Committee regarding updated standards
End of May 2020
Technical Standards published & communicated
Progress update
End of Feb 2020
Q1 2020
(TBC) 1
Technical Standards Steering Committee
Technical Standards Working Group
Technical Standards Steering Committee meeting
Technical Standards Steering Committee meeting
Technical Standards Steering Committee
1Date to be confirmed following completion of 22 November milestone
Review and endorse harmonisation opportunities
(via circulation)